## Test_site_functionality
Level Page Process User story Other | Attempt # | Test item | Description of test | Date of test - Development | Result - Development | Status - Development OK Resolved Ongoing | Date of test - Production | Result - Production | Status - Production OK Resolved Ongoing
Other | 1 | Favicon | Check favicon appears correctly | 2021-07-19 | Icon appears correctly | OK | 2021-07-21 | Favicon appears correctly but is difficult to see against the grey background. Suggest we add a black background for contrast | Ongoing
Other | 1 | Tab title | Check tab title reflects gym name '1UP Bouldering' | 2021-07-19 | Tab title name is correct | OK | 2021-07-21 | OK | OK
Page | 1 | Home page | Check page for any issues | 2021-07-19 | Error message appears because nothing is returned by App.js. Issue addressed by adding logo as temporary placeholder on home page | Resolved | N/A | N/A - home page was temporary placeholder and has now been replaced | OK
Process | 1 | New member sign up | Process should follow the logic of the site map and wireframe prototypes | 2021-07-21 | OK - no issues Process is intuitive and straightforward | OK | 2021-07-21 | OK | OK
Page | 1 | Check In page | Page should render check-in instructions and email field | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK | OK
Page | 1 | Log In page | Page should render log-in instructions, email field, password field and link for password reset | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK | OK
Page | 1 | Sign Up page | Page should prompt for user email, password, password confirmation | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK | OK
Page | 1 | User details page | Page should collect user sign up information and profile image | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK | OK
Other | 1 | Photo upload | Open dialogue box to upload user image Image should preview should display | 2021-07-21 | OK - no issues Image preview displays correctly | OK | 2021-07-21 | OK | OK
Other | 1 | Photo upload | Drag and drop to upload user image Image should preview should display | 2021-07-21 | OK - no issues Image preview displays correctly | OK | 2021-07-21 | OK | OK
Page | 1 | Waiver | Waiver should display and prompt user for signature | 2021-07-21 | OK - Waiver displays correctly | OK | 2021-07-21 | OK | OK
Other | 1 | Signature process | Signature box should appear for user to sign with mouse | 2021-07-21 | OK - Signature field appears and process works as expected. Reset also works. | OK | 2021-07-21 | OK | OK
Page | 1 | Payment page | Monthly or annual subscription options should display | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK | OK
Page | 1 | Forgot password page | Page should render password reset instructions and email field | 2021-07-21 | OK - no issues | OK | 2021-07-21 | OK - Page states an email has been sent but email not received | Resolved
Process | 1 | Reset password | Submitting email should send password reset instructions | 2021-07-24 | OK - no issues | OK | 2021-07-25 | Error - confirmation alert appears but email is not delivered | Resolved
Page | 2 | Forgot password page | Page should render password reset instructions and email field | 2021-07-24 | OK - no issues | OK | 2021-07-24 | Page states email was sent and confirmed email received in hotmail account | Ok
Process | 2 | New member sign up | User onboading process to enter details to create a new account | 2021-07-25 | OK - no issues | OK | 2021-07-25 | Error - Unable to pass first stage of creating account with email and password | OK
Process | 1 | Member check in | Test of existing member check in | 2021-07-25 | OK - no issues | OK | 2021-07-26 | 'Page Not Found' error | Resolved
Process | 1 | Member log in | Test of existing member log in | 2021-07-25 | OK - no issues | OK | 2021-07-26 | Renders empty new user form | Resolved
Process | 2 | Reset password | Test of existing member password reset | 2021-07-25 | OK - no issues | OK | 2021-07-26 | Received email in inbox | OK
Process | 3 | New member sign up | User onboading process to enter details to create a new account | 2021-07-26 | OK - no issues | OK | 2021-07-26 | Can create account and enter most details. Climbing experience levels do not appear in drop down list. Waiver text does not appear. Signature form functions as expected. Does not redirect to external payments. Freezes on profile page | Resolved
Process | 4 | New member sign up | User onboading process to enter details to create a new account | 2021-07-26 | OK - no issues | OK | 2021-07-26 | Payments now works and redirects correctly on successful completion. Experience level and waiver text still do not appear | Resolved
Process | 2 | Member check in | Test of existing member check in | 2021-07-26 | OK - no issues | OK | 2021-07-26 | Check-in feature accepts valid user email and displays a welcome screen. After a short timeout, page redirects to check-in screen ready for the next user | OK
Process | 2 | Member log in | Test of existing member log in | 2021-07-26 | OK - no issues | OK | 2021-07-26 | Successful login. Redirects user to view/edit their own profile page. | OK
Process | 5 | New member sign up | User onboading process to enter details to create a new account | 2021-07-26 | OK - no issues | OK | 2021-07-26 | All issues resolved. New member sign up works as expected | OK
Page | 1 | Check-In dashboard | Page should render a list of members currently at the gym with their contact details, photo, waiver status and check-in time | 2021-07-27 | OK - no issues | OK | 2021-07-27 | Dashboard appears as expected except profile images are missing | Resolved
Page | 2 | Check-In dashboard | Page should render a list of members currently at the gym with their contact details, photo, waiver status and check-in time | 2021-07-27 | OK - no issues | OK | 2021-07-27 | Error message, page renders but no data is returned. Suspected issue of data not returned because some profiles are missing images. | Resolved
Page | 3 | Check-In dashboard | Page should render a list of members currently at the gym with their contact details, photo, waiver status and check-in time | 2021-07-27 | OK - no issues | OK | 2021-07-27 | All data including images appears as expected | Resolved
Other | 2 | Favicon | Check favicon appears correctly | Pending | Pending | Pending | Pending | Pending | Pending
User Story | 1 | As a member, I want to manually check-in with my email or phone number, in case I arrived at the gym without my QR Code. | Test of checking in with valid user input, user@test.com | 2021-07-27 | Check in accepts valid user details and redirects to welcome page. After a short timeout, the page returns to the check-in page ready for the next member. | OK | 2021-07-27 | Check in accepts valid user details and redirects to welcome page. After a short timeout, the page returns to the check-in page ready for the next member. | OK
User Story | 1 | As a member, I want to manually check-in with my email or phone number, in case I arrived at the gym without my QR Code. | Test of checking with invalid user input, wrong@test.com | 2021-07-27 | Alert appears to notify member they cannot be checked in | OK | 2021-07-27 | Alert appears to notify member they cannot be checked in | OK
User Story | 1 | As a member, I want to be able to login/logout to view my dashboard securely. | Test of checking in with valid user input, user@test.com, password | 2021-07-27 | User is logged in successfully. Redirects to edit profile page as expected | OK | 2021-07-27 | User is logged in successfully. Redirects to edit profile page as expected | OK
User Story | 1 | As a member, I want to be able to login/logout to view my dashboard securely. | Test of checking with invalid user input, wrong@test.com, notpassword | 2021-07-27 | Alert appears to notify member they cannot be logged in | OK | 2021-07-27 | Alert appears to notify member they cannot be logged in | OK
User Story | 1 | As an owner, I want an intuitive frictionless sign-up interface, so I can quickly onboard new members. | Test of onboarding new member with all required input included | 2021-07-27 | Seemless and intuitive process, user is notified when account has been created. Payment process is straightforward and redirects correctly. | OK | 2021-07-27 | Seemless and intuitive process, user is notified when account has been created. Payment process is straightforward and redirects correctly. | OK
User Story | 1 | As an owner, I want an intuitive frictionless sign-up interface, so I can quickly onboard new members. | Test of onboarding new member with some expected input missing | 2021-07-27 | Alert appears to notify member they have missed some fields. | OK | 2021-07-27 | Alert appears to notify member they have missed some fields. | OK
User Story | 1 | As an owner, I want to capture individual member profiles, so I can leverage data analytics to improve my service offering. | Member onboarding process collects all required information | 2021-07-27 | Member onboarding process collects member profile information, including location and climbing experience | OK | 2021-07-27 | Member onboarding process collects member profile information, including location and climbing experience | OK
User Story | 1 | As an owner, I want to shoot and store member photos, so I can verify their identity on entry. | Upload member photo during onboarding | 2021-07-27 | Drag and drop and opening dialogue box both work to upload an existing image for a member profile photo | OK | 2021-07-27 | Drag and drop and opening dialogue box both work to upload an existing image for a member profile photo | OK
User Story | 1 | As an owner, I want to shoot and store member photos, so I can verify their identity on entry. | Take new photo during onboarding process | N/A | Taking a photo not available for testing in development environment | OK | 2021-07-27 | Taking a photo during onboarding process confirmed on IOS and Android devices | OK
User Story | 1 | As an owner, I want to display a waiver and collect digital signatures, so I can be sure that my members understand their rights. | Sign waiver during onboarding process | 2021-07-27 | Waiver text appears with a dialogue box to sign using mouse and input field to record name. | OK | 2021-07-27 | Waiver text appears with a dialogue box to sign using mouse or touchscreen and input field to record name. | OK
User Story | 1 | As an owner, I want to use a reputable third party payment system, so my billing process is frictionless and my members can be certain that their details are secure. | Member completes recurring payment set up during onboarding | 2021-07-27 | App redirects user to external payment system (Stripe) during onboarding and redirects them back to the app and confirms payment is successful. | OK | 2021-07-27 | App redirects user to external payment system (Stripe) during onboarding and redirects them back to the app and confirms payment is successful. | OK
User Story | 1 | As an owner, I want a live view of new check-ins, so I can evaluate each member entering the gym at a glance. | View checkin dashboard | 2021-07-27 | Admin dashboard shows view highlighting current member checking in along with list of other currently checked in members with contact details, profile photo, waiver status and check in time | OK | 2021-07-27 | Admin dashboard shows view highlighting current member checking in along with list of other currently checked in members with contact details, profile photo, waiver status and check in time | OK
User Story | 1 | As an owner, I want to login/logout as an admin to view sensitive information and ensure it is properly secured. | Confirm login and logout work and access to admin views is not visible after logging out | 2021-07-27 | Login and logout work. Admin only data such as check-in info is not available after admin has checked out. | OK | 2021-07-27 | Login and logout work. Admin only data such as check-in info is not available after admin has checked out. | OK
User Story | 1 | As an owner, I want to provide multiple membership types, so my members have payment flexibility. | Multiple payment options should be available to members | 2021-07-27 | During onboarding members can choose a monthly payment option or annual payment option. | OK | 2021-07-27 | During onboarding members can choose a monthly payment option or annual payment option. | OK
Process | 3 | New member sign up | User onboading process to enter details to create a new account | 2021-07-26 | OK - no issues | OK | 2021-07-26 | Issue now resolved | OK

## Test_site_layout
Date | User story | Test overview | Result - Mobile | Status - Mobile OK Resolved Ongoing | Result - Tablet | Status - Tablet OK Resolved Ongoing | Result - Desktop | Status - Desktop OK Resolved Ongoing
2021-07-27 | As a member, I want to manually check-in with my email or phone number, in case I arrived at the gym without my QR Code. | Test of login using user@test.com | Check-in screen and welcome screen are clear, text is large and legible, all elements appear clearly. Error message is visible when relevant. | OK | Check-in screen and welcome screen are clear, text is large and legible, all elements appear clearly. Error message is visible when relevant. | OK | Check-in screen and welcome screen are clear, text is large and legible, all elements appear clearly. Error message is visible when relevant. | OK
2021-07-27 | As a member, I want to be able to login/logout to view my dashboard securely. | Test of login using user@test.com, password | Login screen is clear. Input fields automatically scroll up and stay visible when phone keyboard appears | OK | Login screen is clear, all elements are visible, including error message when relevant | OK | Login screen is clear, all elements are visible, including error message when relevant | OK
2021-07-27 | As an owner, I want an intuitive frictionless sign-up interface, so I can quickly onboard new members. | Test of new member sign up | Taking a photo from the phone and uploading it for the profile works perfectly. Input fields all make good use of the available space to be clear and easy to access | OK | Information and images are in proportion to the screen size. No issues identified | OK | All pages are clear and make good use of the available space. No issues. | OK
2021-07-27 | As an owner, I want to capture individual member profiles, so I can leverage data analytics to improve my service offering. | Review of database | N/A - not related to site view/layout | N/A | N/A - not related to site view/layout | N/A | N/A - not related to site view/layout | N/A
2021-07-27 | As an owner, I want to shoot and store member photos, so I can verify their identity on entry. | Upload new profile photo during onboarding | Member is prompted to upload an existing photo or take a photo with the devices built in camera. Image is successfully saved to the database. | OK | Member is prompted to upload an existing photo or take a photo with the devices built in camera. Image is successfully saved to the database. | OK | Member is prompted to upload an existing photo. Image is successfully saved to the database. | OK
2021-07-27 | As an owner, I want to display a waiver and collect digital signatures, so I can be sure that my members understand their rights. | Sign waiver during onboarding | Waiver text is well laid out and easy to read. Signature box uses all available space and is responsive to touch on mobile device. | OK | Waiver text is well laid out and easy to read. Signature box uses all available space and is responsive to touch on mobile device. | OK | Waiver text is well laid out and easy to read. Signature box is large enough for use with mouse. | OK
2021-07-27 | As an owner, I want to use a reputable third party payment system, so my billing process is frictionless and my members can be certain that their details are secure. | Member completes recurring payment set up during onboarding | External payment vendor (Stripe) is fully responsive | OK | External payment vendor (Stripe) is fully responsive | OK | External payment vendor (Stripe) is fully responsive | OK
2021-07-27 | As an owner, I want a live view of new check-ins, so I can evaluate each member entering the gym at a glance. | View of check-in dashboard | Mobile view of checkin dashboard highlights current check-in profile image and details, and list of all checked in members names and profile images as a list | OK | View of current check-in displays correctly with large profile image and all user details. List view of all checked in members requires scrolling to view. Hiding the sidebar menu would address this. | Ongoing | Check-in dashboard highlights currently checking in member and lists all other checked in members in list view including profile image and member information. | OK
2021-07-27 | As an owner, I want to login/logout as an admin to view sensitive information and ensure it is properly secured. | Test of login/logout for admin | Login/logout buttons are clearly visible and function correctly. | OK | Login/logout buttons are clearly visible and function correctly. | OK | Login/logout buttons are clearly visible and function correctly. | OK
2021-07-27 | As an owner, I want to provide multiple membership types, so my members have payment flexibility. | Test of multiple membership options available | 2 membership options are provided - monthly and annual. Both are clearly visible. | OK | 2 membership options are provided - monthly and annual. Both are clearly visible. | OK | 2 membership options are provided - monthly and annual. Both are clearly visible. | OK